TAKMIL FOUNDATION

تکمیل فاؤنڈیشن

─────────────────────────────────

DIGITAL ASSESSMENT DEVELOPMENT PROJECT

Complete Project Plan for Building L1–L11 Assessments

Math  ·  English  ·  Urdu  |  Curriculum  ·  PDF Assessments  ·  YouTube Videos

| Prepared By Shahid Qamar, Founder & CEO | Date April 2026 | Classification Confidential — Internal Use Only |
| --- | --- | --- |

EXECUTIVE SUMMARY TAKMIL Foundation operates 190+ community schools in Pakistan serving out-of-school children through an accelerated 12-level curriculum. This project delivers a complete digital assessment platform covering all 11 active levels across 3 subjects (Math, English, Urdu) — sourced from curriculum documents, paper-based assessments, and educational YouTube videos. Total deliverables: 33 level-subject assessment portals + unlimited topic-based video assessments. Platform: WhatsApp-compatible tablet portals deployed on Railway (Node.js + PostgreSQL). Timeline: 20 weeks ¦ Team: 7 people ¦ Content sources: 3 types

# 1.  Project Overview

## 1.1  Background

TAKMIL Foundation's mission is to bring 26 million out-of-school Pakistani children into education by 2047. Its accelerated learning model compresses primary and middle school content into 12 curriculum levels, delivered through 190+ community-based schools across Pakistan.

Levels 1, 2, and 3 assessments are currently live on the TAKMIL Bot platform — a WhatsApp-compatible, tablet-based assessment system. This project completes the platform by building Levels 4 through 11 across all three subjects, while also establishing a repeatable process for generating topic-based assessments from YouTube educational videos.

## 1.2  What This Project Builds

| Category | Description | Volume |
| --- | --- | --- |
| Level Portals | Full 12-question MCQ assessments for each level-subject combination | 33 portals (11 levels × 3 subjects) |
| Content Sources | Curriculum PDFs + Paper-based Assessment PDFs + YouTube Videos | 3 source types |
| Question Banks | 12 MCQ questions per portal, bilingual English/Urdu, with SVG image library where needed | 396 questions minimum |
| Video Assessments | Topic-specific assessments generated from TAKMIL YouTube lesson videos | Ongoing / unlimited |
| Deployment | All portals live on Railway, accessible via WhatsApp-shared URLs with PIN authentication | 33+ live URLs |

## 1.3  The Three Content Sources

| Source | What It Provides | How Claude Uses It |
| --- | --- | --- |
| 📚 Curriculum PDF | Full syllabus, learning objectives, topic breakdowns per level | Extracts key concepts → generates conceptual MCQ questions |
| 📄 Paper Assessment PDF | Official exam questions, marking schemes, past papers | Converts existing paper questions to digital MCQ format |
| 🎬 YouTube Video | Recorded lessons taught by TAKMIL teachers | Reads transcript → generates questions on taught content |

# 2.  Project Goals & Objectives

## 2.1  Strategic Goals

GOAL 1 — Complete Coverage Every TAKMIL student at every level has access to a digital assessment in Math, English, and Urdu. GOAL 2 — Zero-Hallucination Quality All assessments use the 3-layer architecture that prevents answer leakage into images — a standard proven across L1–L3. GOAL 3 — Teacher Empowerment Teachers can generate and share assessment PINs, view student results, and identify learning gaps without technical knowledge. GOAL 4 — Scalable Content Pipeline Any TAKMIL staff member can generate a new assessment from a YouTube video, PDF, or curriculum document within one working day — with or without developer support.

## 2.2  Measurable Objectives

| # | Objective | Metric | Target |
| --- | --- | --- | --- |
| 1 | Complete all 33 level-subject portals | Portals live on Railway | 33 of 33 by Week 16 |
| 2 | Question accuracy verified by subject teachers | Teacher sign-off per portal | 100% of portals teacher-approved |
| 3 | All portals pass quality checklist | QA checklist items passed | 100% pass rate |
| 4 | Video assessment pipeline operational | Assessments built from YouTube videos | 5 video assessments as pilot |
| 5 | Team trained and self-sufficient | Team can build portal without Shahid | By Week 4 |
| 6 | All portals load under 3 seconds | Browser load time test | < 3 sec on 3G connection |
| 7 | Zero answer leakage in images | Manual image review | 0 violations across all portals |

# 3.  Project Scope

## 3.1  In Scope

- Assessment portals for Levels 4–11, all three subjects (24 new portals)

- Rebuilding or reviewing L1–L3 portals if gaps are found during QA

- SVG image libraries for visual/picture questions per level

- YouTube video assessment pipeline (transcript → questions → portal)

- PIN generation and management for all new portals

- Quality assurance checklist and sign-off process

- Team training and documentation

- Deployment to Railway production environment

## 3.2  Out of Scope

- Changes to the WhatsApp bot infrastructure

- Student data analytics dashboard (Phase 2)

- Student-facing mobile app development

- Translation of existing English content to Urdu (separate project)

- Video production (YouTube videos must already exist)

## 3.3  Assessment Portal Completion Matrix

| Level | Math Portal | English Portal | Urdu Portal | Source Material | Status |
| --- | --- | --- | --- | --- | --- |
| L1 | ✅ Live | ✅ Live | ✅ Live | Curriculum PDF | 🟢 Complete |
| L2 | ✅ Live | ✅ Live | ✅ Live | Curriculum PDF | 🟢 Complete |
| L3 | ✅ Live | ✅ Live | ✅ Live | Curriculum PDF | 🟢 Complete |
| L4 | 🔴 Build | 🔴 Build | 🔴 Build | PDF + Video | 🔴 This Project |
| L5 | 🔴 Build | 🔴 Build | 🔴 Build | PDF + Video | 🔴 This Project |
| L6 | 🔴 Build | 🔴 Build | 🔴 Build | PDF + Video | 🔴 This Project |
| L7 | 🔴 Build | 🔴 Build | 🔴 Build | PDF + Video | 🔴 This Project |
| L8 | 🔴 Build | 🔴 Build | 🔴 Build | PDF + Video | 🔴 This Project |
| L9 | 🔴 Build | 🔴 Build | 🔴 Build | PDF + Video | 🔴 This Project |
| L10 | 🔴 Build | 🔴 Build | 🔴 Build | PDF + Video | 🔴 This Project |
| L11 | 🔴 Build | 🔴 Build | 🔴 Build | PDF + Video | 🔴 This Project |
| TOTALS | 11 portals | 11 portals | 11 portals | — | 33 portals |

# 4.  Team Structure & Roles

The project requires 7 people working across 5 distinct roles. Some roles may be combined depending on availability. Each role has clear responsibilities and does not require advanced technical knowledge — the AI-powered pipeline (Claude) handles the heavy lifting.

| Role | No. of People | Weekly Hours |
| --- | --- | --- |
| Project Manager | 1 | 10–15 hrs |
| Content Developer (Urdu/Math/English specialist) | 3 (one per subject) | 20–25 hrs each |
| AI Prompt Operator | 1 | 25–30 hrs |
| Quality Assurance Reviewer | 1 | 15–20 hrs |
| Deployment Engineer | 1 (Shahid or delegate) | 5–8 hrs |
| TOTAL | 7 people | ~105–130 hrs/week |

## 4.1  Role Descriptions

| PROJECT MANAGER | Oversees entire project timeline and milestone delivery. Assigns levels to content developers each week. Tracks progress on the Level Completion Matrix (Google Sheet). Escalates blockers to Shahid. Runs weekly team check-in. Maintains the master PIN registry — which PINs go to which school. Skills needed: communication, Google Sheets, basic project planning. |
| --- | --- |

| CONTENT DEVELOPER (×3) | One developer per subject: Math specialist, English specialist, Urdu specialist. Reads curriculum PDF and past assessment PDFs for their subject. Reviews question spreadsheets generated by Claude — corrects errors. Reviews image library — flags any image containing answer text. Signs off on questions and images before portal assembly. For Urdu developer: must be a fluent Urdu native speaker/reader. Skills needed: subject knowledge, Urdu literacy (for Urdu dev), attention to detail. |
| --- | --- |

| AI PROMPT OPERATOR | Primary Claude.ai user — runs all 5 steps of the build process for each level. Uploads PDFs and YouTube transcripts to Claude. Prompts Claude to generate question spreadsheets, image libraries, and portals. Enters corrections from content developers back into Claude. Downloads all output files and hands to Deployment Engineer. Manages Claude session summaries — pastes handover at start of each chat. Skills needed: Claude.ai usage, copy-paste workflow, file management, English literacy. |
| --- | --- |

| QA REVIEWER | Tests every portal before it goes live using the 20-item QA checklist. Verifies PIN login, question shuffle, scoring, timer, teacher report. Tests in Chrome browser — checks Urdu font rendering. Tests on mobile (tablet/phone) for responsive display. Fills in the QA sign-off sheet — no portal deploys without QA signature. Skills needed: methodical testing, Chrome browser, basic tablet usage. |
| --- | --- |

| DEPLOYMENT ENGINEER | Receives final HTML file from AI Prompt Operator. Copies file to project folder, adds route to index.js. Runs git add → commit → push. Monitors Railway deploy status. Generates PINs using curl command (Math, English, Urdu per level). Saves PINs to registry file, shares with Project Manager. Skills needed: Git, terminal/command prompt, Railway dashboard, curl commands. |
| --- | --- |

# 5.  Skills Required

## 5.1  Technical Skills

| Skill | Who Needs It | Level Required | How to Learn |
| --- | --- | --- | --- |
| Claude.ai — prompt writing | AI Prompt Operator (primary), PM (basic) | Intermediate | 1-day practice on claude.ai — follow this guide |
| Git — add, commit, push | Deployment Engineer | Basic | 30-min tutorial at git-scm.com |
| GitHub — pull requests | Deployment Engineer | Basic | GitHub's own 'Hello World' guide |
| Railway dashboard | Deployment Engineer | Basic | Railway docs at railway.app/docs |
| curl command (terminal) | Deployment Engineer | Basic | Copy-paste from this document |
| Google Sheets — tracking | Project Manager | Intermediate | Already standard knowledge |
| Chrome browser — DevTools | QA Reviewer | Basic | F12 key → Console tab for errors |
| PDF reading tools | Content Developers | Basic | Adobe Acrobat or any PDF viewer |
| YouTube transcript extraction | AI Prompt Operator | Basic | YouTube → ... → Open Transcript |

## 5.2  Subject Knowledge Skills

| Subject Role | Required Knowledge | Critical Qualification |
| --- | --- | --- |
| Math Content Developer | TAKMIL L4–L11 Math curriculum: arithmetic, fractions, geometry, basic algebra | Ability to verify if MCQ questions are grade-appropriate |
| English Content Developer | TAKMIL L4–L11 English curriculum: grammar, comprehension, vocabulary, writing | Native or near-native English fluency |
| Urdu Content Developer | TAKMIL L4–L11 Urdu curriculum: حروف, جوڑ توڑ, قواعد, تحریر | Must be Urdu literate — can read and write Nastaliq script |
| QA Reviewer | Understanding of all 3 subjects at primary/middle level | Ability to spot wrong answers and unclear questions |

## 5.3  Language Skills

- Urdu (native/fluent): Required for Urdu Content Developer. Essential for verifying Urdu question text, Nastaliq script accuracy, and grammar.

- English (proficient): Required for AI Prompt Operator and Project Manager. All Claude prompts are written in English.

- Bilingual (English + Urdu): Ideal for QA Reviewer — must verify both language versions of each question.

# 6.  Tools & Technology Stack

## 6.1  Core Tools — Required

| Tool | Purpose | Who Uses It | Cost |
| --- | --- | --- | --- |
| Claude.ai (Pro plan) | Generate questions, images, portals from PDFs and videos | AI Prompt Operator | $20/month per seat |
| GitHub | Version control — stores all portal files | Deployment Engineer | Free |
| Railway | Hosting platform — auto-deploys on git push | Deployment Engineer | ~$5/month (existing) |
| Chrome Browser | Testing portals, viewing QA results | QA Reviewer, all | Free |
| Git (command line) | Push code to GitHub | Deployment Engineer | Free |
| Google Sheets | Project tracking, PIN registry, progress matrix | Project Manager | Free (Google account) |
| WhatsApp | Share portal URLs and PINs with school coordinators | Project Manager | Free |
| Any text editor (VS Code) | Edit index.js to add new routes | Deployment Engineer | Free |

## 6.2  Content Sourcing Tools

| Tool | Purpose | How to Use |
| --- | --- | --- |
| YouTube (youtube.com) | Source educational videos from TAKMIL channel | Open video → click ••• → Open Transcript → Copy all text |
| Adobe Acrobat / any PDF viewer | Read curriculum and assessment PDFs | Open PDF → upload to Claude as file attachment |
| Google Drive (shared folder) | Team file sharing — PDFs in, HTML files out | Shahid creates shared folder with all source PDFs per level |
| Loom / screen recording | Document bugs found during QA | Record browser screen → share link with AI Operator for fixing |

## 6.3  Technology Architecture (for reference)

TAKMIL Bot Platform Stack Frontend: HTML5 + CSS3 + Vanilla JavaScript (single-file portals, offline-capable) Backend: Node.js + Express.js (Railway deployment) Database: PostgreSQL (Railway managed) — PIN storage, session tracking, results Messaging: Twilio WhatsApp API (sandbox: join gone-dawn) Fonts: Google Noto Nastaliq Urdu (loaded via CDN for Urdu text rendering) Images: Inline SVG (no external image hosting — works offline) AI Engine: Claude.ai (claude-sonnet) via claude.ai interface (not API) Portal URL pattern: https://takmil-bot-production-0f51.up.railway.app/level[N] Admin endpoint: /admin/pins/generate (curl POST — see Section 7)

# 7.  The 5-Step Build Process

Every assessment portal — regardless of source material (curriculum PDF, paper assessment, or YouTube video) — follows this same 5-step process. One level = one focused work session, typically 3–4 hours.

| Step | Action | Who Does It | Output | Gate |
| --- | --- | --- | --- | --- |
| 1 | Upload source material to Claude (PDF or YouTube transcript) | AI Prompt Operator | Claude confirms content read | — |
| 2 | Generate question spreadsheet (12 MCQ per subject, bilingual) | AI Prompt Operator + Content Developer | HTML review table | ⛔ Teacher MUST approve before Step 3 |
| 3 | Build SVG image library (visual questions only) | AI Prompt Operator | HTML image preview file | — |
| 4 | Image review — check for answer leakage in visuals | Content Developer + QA Reviewer | Corrected image library | ⛔ Teacher MUST approve before Step 5 |
| 5 | Assemble portal + deploy + generate PINs | AI Operator + Deployment Engineer | Live URL + PINs list | QA checklist must pass |

## 7.1  Source-Specific Process Notes

| Source | Step 1 Action | Special Considerations |
| --- | --- | --- |
| Curriculum PDF | Upload PDF to Claude. Say: 'Extract 12 MCQ questions for Level X [Subject] from this curriculum.' | Questions test conceptual understanding. Claude may need guidance on which chapter/topic to focus on. |
| Paper Assessment PDF | Upload PDF to Claude. Say: 'Convert these paper exam questions into MCQ digital format for Level X [Subject].' | Some paper questions are open-ended — Claude will convert to MCQ. Review carefully that options are plausible. |
| YouTube Video | Go to video → click ••• → Open Transcript → copy all text. Paste into Claude. Say: 'Generate 12 MCQ questions from this lesson transcript for Level X [Subject].' | Transcript may contain filler words (um, uh, ok class). Claude filters these automatically. Verify questions match what was actually taught. |

# 8.  Project Milestones & Timeline

Total project duration: 20 weeks. The team builds 2 levels per week from Week 3 onward (6 portals/week = 2 levels × 3 subjects). Weeks 1–2 are setup and training.

| Week | Activity | Levels | Portals | Owner |
| --- | --- | --- | --- | --- |
| 1 | Team onboarding, tool access, training on 5-step process | — | — | PM + Shahid |
| 2 | Pilot build: L4 Math together as a team (supervised practice) | L4 Math | 1 | Full team |
| 3 | L4 English + L4 Urdu | L4 | 2 more | Team |
| 4 | L5 Math + L5 English + L5 Urdu | L5 | 3 | Team |
| 5 | L6 Math + L6 English + L6 Urdu | L6 | 3 | Team |
| 6 | L7 Math + L7 English + L7 Urdu | L7 | 3 | Team |
| 7 | L8 Math + L8 English + L8 Urdu | L8 | 3 | Team |
| 8 | L9 Math + L9 English + L9 Urdu | L9 | 3 | Team |
| 9 | L10 Math + L10 English + L10 Urdu | L10 | 3 | Team |
| 10 | L11 Math + L11 English + L11 Urdu | L11 | 3 | Team |
| 11–12 | QA review of all 33 portals — fix issues | All | — | QA Reviewer |
| 13–14 | YouTube video assessment pilot (5 topic videos) | Topics | 5 | AI Operator |
| 15–16 | Final fixes, re-testing flagged portals | All | — | Full team |
| 17–18 | Deploy all remaining portals, generate all PINs | All | — | Deployment Eng. |
| 19–20 | School coordinator training, go-live support | — | — | PM + Shahid |

## 8.1  Milestone Summary

| M 1 | Team Ready & Trained [Week 1–2] → All 7 team members have GitHub, Railway, and Claude.ai access → 5-step build process understood by all roles → Google Sheets tracking template set up → Source PDF folder shared with all developers → Pilot build: L4 Math portal completed as supervised practice |
| --- | --- |

| M 2 | Levels 4–7 Complete [Week 3–6] → 12 assessment portals live (L4 Math/English/Urdu through L7 Math/English/Urdu) → All portals teacher-approved and QA-passed → PINs generated and shared with school coordinators → Team operating independently (no Shahid involvement in day-to-day) |
| --- | --- |

| M 3 | Levels 8–11 Complete [Week 7–10] → All 33 assessment portals live — full coverage L1 to L11 → Complete 33-portal QA sign-off matrix completed → All PINs generated, saved, and distributed → Zero answer-leakage violations confirmed |
| --- | --- |

| M 4 | YouTube Video Pipeline Live [Week 11–14] → 5 topic-based video assessments built and deployed → Process documented: any team member can build from a new YouTube video in < 1 day → Template Claude prompt for video assessments finalized |
| --- | --- |

| M 5 | Full Platform Go-Live [Week 17–20] → All portals accessible at live URLs and tested on real tablets → School coordinators trained on PIN sharing and student assessment flow → Project handover to operations team → Post-launch support period begins (2 weeks buffer for issues) |
| --- | --- |

# 9.  Quality Assurance Framework

## 9.1  Two-Gate Review System

No portal advances to the next step without a named person signing off. Two gates exist in the pipeline:

| Gate | When | Who Signs Off | What They Check |
| --- | --- | --- | --- |
| Gate 1 — Question Approval | After Step 2 (question spreadsheet) | Subject Content Developer | Correct answers, grade-appropriate language, Urdu accuracy, no duplicates from lower levels |
| Gate 2 — Image Approval | After Step 4 (image library) | Content Developer + QA Reviewer | Zero answer text in images, correct visual content (e.g. correct time on clock), clean SVG rendering |

## 9.2  QA Checklist (20 Items)

The QA Reviewer must pass all 20 items for every portal before it deploys.

| # | Category | Check Item |
| --- | --- | --- |
| 1 | Questions | All 12 questions are grade-appropriate for this level |
| 2 | Questions | All 4 answer options are plausible (wrong answers are not obviously wrong) |
| 3 | Questions | Correct answer verified by subject teacher |
| 4 | Questions | No question duplicated from a lower level portal |
| 5 | Questions | No spelling errors in English question text |
| 6 | Urdu | Urdu text verified by native Urdu speaker |
| 7 | Urdu | Urdu Nastaliq font renders correctly in Chrome |
| 8 | Urdu | All Urdu text is right-to-left and displays correctly |
| 9 | Images | Every image ID in question bank has a matching SVG in image library |
| 10 | Images | No image contains text that is also an answer option |
| 11 | Images | Visual content is factually correct (clocks, counts, shapes, letters) |
| 12 | Portal — Function | PIN login accepts valid PINs and rejects invalid ones |
| 13 | Portal — Function | Subject selection shows all applicable subjects |
| 14 | Portal — Function | Questions shuffle on each new session (test twice) |
| 15 | Portal — Function | Timer counts down correctly from set time |
| 16 | Portal — Function | Score % calculates correctly (test with known answers) |
| 17 | Portal — Function | Pass/fail threshold is 70% — confirmed |
| 18 | Portal — Function | Teacher report shows correct/wrong for each question |
| 19 | Portal — Function | Portal works offline (disconnect Wi-Fi, reload — still works) |
| 20 | Deployment | Live URL loads without errors — tested on tablet |

# 10.  Risks & Mitigation

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Urdu text errors not caught before deployment | Medium | High — students see wrong text | Mandatory native Urdu speaker review at Gate 1. QA Reviewer also verifies Urdu rendering. |
| Answer leakage in SVG images | Medium | High — students see answer in image | 3-layer architecture prevents this by design. Gate 2 review adds a human check. |
| Claude generates inaccurate questions | Low-Medium | High | Teacher content review at Gate 1. Questions sourced from official curriculum PDFs, not generated freely. |
| Team member unavailable mid-project | Medium | Medium | Document everything in session summaries. Two people trained per role where possible. |
| YouTube transcript unavailable | Low | Low | Fall back to curriculum PDF or paper assessment PDF as alternate source. |
| Railway deployment failure | Low | Low | Deployment Engineer monitors Railway dashboard. Rollback is one git revert command. |
| Timeline overrun | Medium | Medium | 2 portal buffer weeks built into schedule (weeks 15–16). PM escalates early if falling behind. |

# 11.  Budget Estimate

| Item | Unit Cost | Units | Total (20 weeks) | Notes |
| --- | --- | --- | --- | --- |
| Claude.ai Pro (AI Operator) | $20/month | 1 seat | $40 | 2 months subscription |
| Claude.ai Pro (QA/PM if needed) | $20/month | 1 seat | $40 | Optional — free tier may suffice |
| Railway hosting (existing) | ~$5/month | 1 | $10 | Already live — marginal increase |
| Google Workspace / Drive | $0 | 1 | $0 | Free tier sufficient |
| Developer time (7 people × 20 weeks) | PKR cost | 7 people | Project-specific | Costed separately per HR plan |
| TECH TOOLS TOTAL | — | — | ~$90 USD | Excluding human resources |

💡 Key insight: The technology cost for this entire 20-week project is under $100 USD. The primary investment is team time. The AI-powered pipeline (Claude) dramatically reduces the effort required to generate 396+ assessment questions from scratch.

# 12.  Success Metrics & KPIs

| KPI | Baseline (Today) | Target (Week 20) | Measurement Method |
| --- | --- | --- | --- |
| Active assessment portals | 3 portals (L1–L3) | 33+ portals (L1–L11 + topics) | Count of live Railway URLs |
| Students assessable digitally | L1–L3 only | All 11 levels, all subjects | Portal coverage matrix |
| Assessment creation time (new level) | 3–5 days (with Shahid) | < 1 day (any team member) | Time tracked from PDF upload to live URL |
| Question accuracy rate | Estimated 95%+ (L1–L3) | 100% teacher-verified | Gate 1 sign-off records |
| QA pass rate (first attempt) | N/A | > 90% pass on first QA | QA checklist records |
| Image answer-leakage violations | 0 (L1–L3) | 0 (all portals) | Manual Gate 2 review log |
| School coordinators using portals | Schools with L1–L3 access | All 190 schools with full access | Railway PIN usage logs |

# 13.  Quick Reference — Commands & URLs

## Live System

Bot: https://takmil-bot-production-0f51.up.railway.app Dashboard: https://takmil-bot-production-0f51.up.railway.app/dashboard L1 Portal: https://takmil-bot-production-0f51.up.railway.app/pdf-portal L2 Portal: https://takmil-bot-production-0f51.up.railway.app/level2 L3 Portal: https://takmil-bot-production-0f51.up.railway.app/level3 Next target: https://takmil-bot-production-0f51.up.railway.app/level4

## PIN Generation Command

curl -X POST https://takmil-bot-production-0f51.up.railway.app/admin/pins/generate \ -H "Content-Type: application/json" \ -d '{"schoolId":1,"level":4,"subject":"Math","cohortSize":30,"issuedBy":"YourName"}' → Change level (4–11) and subject (Math / English / Urdu) for each run. → Run 3 times per level (once per subject). Save output PINs to file.

## Deployment Command Sequence

git add takmil-level[N]-portal.html index.js git commit -m "Add Level [N] assessment portal" git push origin main # Then watch Railway dashboard for 'Deploy success' (1–2 minutes)

## index.js Route to Add (per new level)

app.get('/level[N]', (req,res) => res.sendFile(path.join(__dirname,'takmil-level[N]-portal.html')));

PROJECT APPROVED BY: Shahid Qamar ¦ Founder & CEO, TAKMIL Foundation DATE: April 2026 VERSION: 1.0 — Initial Project Plan This document is confidential and intended for internal TAKMIL team use only. Do not distribute outside the project team without written approval from Shahid Qamar.