TAKMIL FOUNDATION

تکمیل فاؤنڈیشن

────────────────────────────────

VIDEO-TO-ASSESSMENT PIPELINE

Full Project Requirements, Skills, Tools & Team Guide

From YouTube Lesson Video → Approved Questions → Live Student Assessment

| Prepared By Shahid Qamar | Date April 2026 | Scope 190 Schools · All Levels | Status Ready to Execute |
| --- | --- | --- | --- |

WHAT THIS PROJECT DOES Every TAKMIL lesson video becomes a verified student assessment — automatically. A facilitator runs 3 videos per day. When a section (topic block) is complete, an assessment is unlocked. The assessment is built from the exact videos the students watched. This document gives your team EVERYTHING they need to finish this project: requirements · skills · tools · step-by-step process · team roles · quality standards

# 1.  Project Overview

## 1.1  What This Project Builds

The TAKMIL Video-to-Assessment Pipeline connects three things that currently exist separately:

| Component | What It Is | Status |
| --- | --- | --- |
| TAKMIL Bot | WhatsApp-based student assessment system on Railway | ✅ Live |
| Assessment Portals | L1–L3 tablet MCQ portals (L4–L11 in progress) | 🟡 Partial |
| Video Player | Laptop/projector app — runs USB or YouTube videos | ✅ Built |
| Ops Console | Web dashboard — 4-role testing and approval system | ✅ Built |
| Video-to-Assessment | Turns any lesson video into a verified MCQ assessment | 🔴 Your team builds this |

## 1.2  The Core Idea

BEFORE (manual, slow, error-prone): Teacher writes questions from scratch → sends to Shahid → Shahid reviews → months pass AFTER (this project): Paste YouTube link into Claude → 12 questions generated in 2 minutes → Teacher reviews → approved → portal deployed → students assessed the same day One video → one assessment → same day. Repeatable. Scalable. Quality-controlled.

## 1.3  Scale of the Work

| What | Number | How Generated |
| --- | --- | --- |
| TAKMIL lesson videos (estimated) | 300–500 | Already exist on YouTube channel |
| Levels × Subjects × Sections | 11 × 3 × ~8 sections each | = ~264 assessment portals total |
| Questions per portal | 12 MCQ | Claude generates from video transcript |
| Languages per question | 2 (English + Urdu) | Claude generates both simultaneously |
| SVG images per portal | 0–8 (visual questions only) | Claude draws in zero-hallucination format |
| Portals already complete (L1–L3) | 9 | Already deployed on Railway |
| Portals your team must complete | 255+ | This project |

# 2.  The 5-Step Process  (Every Video Follows This)

Every single assessment — whether from a YouTube video, curriculum PDF, or paper assessment — follows these exact 5 steps. No exceptions. No shortcuts.

| STEP 1 | Find the Video & Paste the Link → Content Developer locates the TAKMIL YouTube lesson video for this topic → Copies the YouTube URL: https://www.youtube.com/watch?v=XXXXXXXXX → Opens Claude.ai → starts a new chat → pastes the session summary document → Tells Claude: 'Build assessment for Level [X] [Subject]. Video: [URL]' → Claude fetches the video transcript/description automatically |
| --- | --- |

| STEP 2 | Generate Question Spreadsheet — Teacher Reviews FIRST → Claude generates 12 MCQ questions based on what was taught in the video → Output: HTML table — Q#, question in English, question in Urdu, options A–D, correct answer highlighted → Content Developer sends this table to the Subject Teacher for review → Teacher corrects any errors: 'Q4 answer should be B not C' → Claude regenerates with corrections → GATE 1: Teacher gives written approval before ANY images are drawn |
| --- | --- |

| STEP 3 | Build Image Library (only if visual questions exist) → For questions that reference shapes, diagrams, clocks, objects — Claude draws SVGs → ZERO answer text in any image — enforced by 3-layer architecture → Claude outputs one HTML file: all images displayed side by side with IDs → Content Developer opens file in browser and checks every image visually → GATE 2: Teacher approves images before portal is assembled → If no visual questions: skip this step entirely |
| --- | --- |

| STEP 4 | Assemble the Assessment Portal → Claude assembles the 3-layer portal: question bank + image library + assessment engine → Output: one HTML file named takmil-[topic]-[level]-portal.html → Content Developer opens file in Chrome and runs the full QA checklist (20 items) → Fix any issues → rerun QA → pass all 20 items → QA Reviewer signs off on the portal before deployment |
| --- | --- |

| STEP 5 | Deploy & Link to Video Session → Deployment Engineer copies HTML file to Railway project folder → Adds route to index.js: app.get('/topic-name', ...sendFile(...)) → git add → commit → push → Railway auto-deploys → Generates PINs: Math + English + Urdu per section → Links assessment to video section in database → Assessment automatically unlocks for a school when their video sessions are complete |
| --- | --- |

# 3.  Three Content Sources

Assessments can be built from three sources. The 5-step process is identical — only Step 1 changes.

| Source | Step 1 Action | Best For | Claude Prompt |
| --- | --- | --- | --- |
| YouTube Video | Paste URL → Claude reads transcript | Lessons already recorded on TAKMIL channel | 'Level 5 Math. Video: [URL]. Build assessment.' |
| Curriculum PDF | Upload PDF → Claude extracts key concepts | New topics not yet on video | 'Level 5 Math. Curriculum attached. Build 12 MCQ.' |
| Paper Assessment PDF | Upload PDF → Claude converts to digital MCQ | Existing paper exams | 'Convert this paper exam to digital MCQ format.' |

# 4.  Team Structure & Roles

The project requires 6 people. Each role is clearly separated. No one needs to know everything — they only need to know their step.

| Role | People | Hours/Week | Owns Which Steps |
| --- | --- | --- | --- |
| Project Manager | 1 | 10–15 hrs | Assigns work · tracks progress · escalates blockers |
| Content Developer — Math | 1 | 20–25 hrs | Steps 1–2 for all Math assessments |
| Content Developer — English | 1 | 20–25 hrs | Steps 1–2 for all English assessments |
| Content Developer — Urdu | 1 | 20–25 hrs | Steps 1–2 for all Urdu assessments (must be native Urdu speaker) |
| QA Reviewer | 1 | 15–20 hrs | Steps 3–4: image check + 20-item QA checklist |
| Deployment Engineer | 1 | 8–10 hrs | Step 5: Railway deployment + PIN generation |
| TOTAL | 6 people | ~100 hrs/week | — |

## 4.1  Role Descriptions

| PROJECTMANAGER | Maintains master tracker in Google Sheets: one row per video, status of each step Assigns videos to content developers each Monday Runs weekly 30-min check-in with full team Escalates to Shahid when: a video has no transcript · a question is disputed · Railway is down Maintains PIN registry: which PINs go to which school coordinator Skills: Google Sheets, communication, basic project planning |
| --- | --- |

| CONTENTDEVELOPER(× 3) | One developer per subject: Math · English · Urdu Locates the correct YouTube video for each topic from TAKMIL's video library Runs Steps 1–2: pastes link into Claude, gets question spreadsheet, sends to teacher Collects teacher corrections, tells Claude to fix, gets approval Sends approved questions + image library (if needed) to QA Reviewer Urdu developer MUST be a native Urdu reader — can verify Nastaliq script accuracy Skills: Claude.ai usage · subject knowledge · Urdu literacy (Urdu dev) · attention to detail |
| --- | --- |

| QAREVIEWER | Receives portal HTML from Content Developer after teacher approval Runs the full 20-item QA checklist in Chrome browser Checks images: ZERO answer text allowed — flags any violation immediately Tests: PIN login · question shuffle · scoring · timer · teacher report · Urdu font rendering Tests on mobile/tablet — confirms responsive display Fills QA sign-off sheet — no portal goes to deployment without QA signature Skills: methodical testing · Chrome browser · basic tablet usage · bilingual check (EN + UR) |
| --- | --- |

| DEPLOYMENTENGINEER | Receives QA-approved HTML file from QA Reviewer Copies file to Railway project folder alongside index.js Adds route to index.js, runs git add → commit → push Monitors Railway dashboard for successful deployment Generates PINs via curl command (Math, English, Urdu per section) Links assessment section to video sessions in PostgreSQL database Saves PINs to registry file, shares with Project Manager Skills: Git · terminal/command prompt · Railway dashboard · curl commands · SQL basics |
| --- | --- |

# 5.  Skills Required

## 5.1  Technical Skills

| Skill | Who Needs It | Level | How to Get It |
| --- | --- | --- | --- |
| Claude.ai — prompt engineering | All Content Developers (primary), PM (basic) | Intermediate | 1-day practice. Use session summary at start of each chat. |
| Git — add, commit, push | Deployment Engineer | Basic | 30-min tutorial at git-scm.com/book |
| GitHub — repo access | Deployment Engineer | Basic | Shahid adds as collaborator |
| Railway — dashboard & deploy | Deployment Engineer | Basic | railway.app/docs — 1 hour to learn |
| PostgreSQL — basic queries | Deployment Engineer | Basic | Copy-paste SQL from this document |
| curl command (terminal) | Deployment Engineer | Basic | Copy-paste from PIN generation guide |
| Chrome DevTools (F12) | QA Reviewer | Basic | F12 → Console tab — look for red errors |
| Google Sheets | Project Manager | Intermediate | Standard office skill |
| YouTube — transcript extraction | All Content Developers | Basic | Video → ··· → Open Transcript → Copy |

## 5.2  Subject Knowledge Skills

| Role | Required Knowledge | Critical Test |
| --- | --- | --- |
| Math Content Developer | TAKMIL L1–L11 curriculum: arithmetic, fractions, geometry, algebra, word problems | Can you tell if a math MCQ is correct and grade-appropriate? |
| English Content Developer | TAKMIL L1–L11 curriculum: phonics, grammar, comprehension, vocabulary, writing | Are you fluent enough to spot unnatural English in a question? |
| Urdu Content Developer | TAKMIL L1–L11 curriculum: حروف، جوڑ توڑ، قواعد، تحریر، ادب | Can you READ and WRITE Urdu Nastaliq script fluently? |
| QA Reviewer | Basic competency in all 3 subjects at primary/middle level | Can you spot a wrong answer or unclear question in any subject? |

## 5.3  Language Skills

- Urdu (native/fluent): REQUIRED for Urdu Content Developer. Cannot be substituted. Every Urdu question must be verified by a native Urdu reader before teacher approval.

- English (proficient): Required for all Claude prompts and coordination. All Claude prompts are written in English.

- Bilingual (English + Urdu): Ideal for QA Reviewer — must verify both language versions of every question in every portal.

# 6.  Tools Required

## 6.1  Core Tools — Every Team Member Needs These

| Tool | Purpose | Who Uses It | Cost | How to Get |
| --- | --- | --- | --- | --- |
| Claude.ai (Pro plan) | Generate questions, images, portals from videos and PDFs | All Content Developers | $20/month per seat | claude.ai → subscribe |
| Chrome Browser | Test portals, view QA checklist results | QA Reviewer + all | Free | Already installed |
| Google Sheets | Project tracking, progress matrix, PIN registry | Project Manager | Free | Google account |
| WhatsApp | Coordinate team, share PINs with school coordinators | Project Manager | Free | Already on phones |
| Git + GitHub | Version control, deploy to Railway | Deployment Engineer | Free | git-scm.com |
| VS Code (any text editor) | Edit index.js to add new routes | Deployment Engineer | Free | code.visualstudio.com |

## 6.2  Platform Tools — Already Running

| Platform | What It Does | URL / Access |
| --- | --- | --- |
| Railway | Hosts the bot, database, and all assessment portals | railway.app — Shahid adds team members |
| PostgreSQL (on Railway) | Stores schools, PINs, sessions, results, video logs | Query tab in Railway dashboard |
| Twilio WhatsApp API | Sends WhatsApp messages to facilitators, coordinators, parents | twilio.com — existing account |
| TAKMIL Bot (live) | The running system: https://takmil-bot-production-0f51.up.railway.app | Already deployed — do not break |
| Ops Console | Web-based role-switching test dashboard | takmil-bot-production-0f51.up.railway.app/console |

## 6.3  Content Creation Tools

| Tool | Purpose | Used In Step |
| --- | --- | --- |
| TAKMIL Session Player (HTML file) | Runs videos in classroom — USB or YouTube — generates completion codes | Daily classroom use |
| Claude.ai | Generates questions, images, portal from video/PDF | Steps 1–4 |
| YouTube | Source of lesson videos — transcript extraction | Step 1 |
| Google Drive (shared folder) | Team file sharing: PDFs in, HTML portals out | All steps |
| Loom (or any screen recorder) | Document bugs found during QA — share with Content Developer | Step 4 |

# 7.  Exact Claude Prompts to Use

Use these EXACT phrases at each step. Always paste the session summary at the start of every new Claude chat.

Starting a new assessment (YouTube video):

'Here is my project summary: [paste session summary]. I want to build a Level [X] [Subject] assessment. The lesson video is: https://www.youtube.com/watch?v=XXXXXXXXX Please read the video content and generate the question spreadsheet.'

Starting from a curriculum PDF:

'Here is my project summary: [paste session summary]. I want to build a Level [X] [Subject] assessment from this curriculum. [Upload PDF file] Extract the key learning objectives and generate 12 MCQ questions.'

Sending corrections after teacher review:

'Here are teacher corrections: - Q3: answer should be B not A - Q7: option C wording unclear, change to: running quickly - Q11 Urdu: typo, correct text is: [correct Urdu] Please regenerate the spreadsheet with these corrections.'

After question approval — requesting images:

'Questions approved by teacher. Now build the image library for this assessment. Output one HTML file with all SVG images displayed side by side. Remember: zero answer text in any image.'

After image approval — assembling portal:

'Images approved. Assemble the assessment portal. Output as: takmil-[topic]-level[X]-portal.html Use the same 3-layer architecture as Level 3.'

If something looks wrong in the portal:

'In the portal, [describe the issue]. Examples: - The Urdu text is not right-to-left - Score shows 75% but should be 67% (8 out of 12) - Image clock_1030 shows wrong time'

# 8.  Quality Assurance — 20-Item Checklist

The QA Reviewer must pass ALL 20 items for EVERY portal. No exceptions. No portal deploys without this signed off.

| # | Category | Check Item | Pass / Fail |
| --- | --- | --- | --- |
| 1 | Questions | All 12 questions are grade-appropriate for this level |  |
| 2 | Questions | All 4 answer options are plausible — wrong answers not obviously wrong |  |
| 3 | Questions | Correct answer verified by subject teacher (written sign-off) |  |
| 4 | Questions | No question duplicated from a lower-level portal |  |
| 5 | Questions | No spelling errors in English question text |  |
| 6 | Urdu | Urdu text verified by native Urdu speaker |  |
| 7 | Urdu | Noto Nastaliq Urdu font renders correctly in Chrome |  |
| 8 | Urdu | All Urdu text is right-to-left — no left-to-right mixing |  |
| 9 | Urdu | Questions match the video content — not generic Urdu grammar |  |
| 10 | Images | Every image ID in question bank has a matching SVG in library |  |
| 11 | Images | No image contains text that is also an answer option |  |
| 12 | Images | Visual content is factually correct (clocks, counts, shapes, letters) |  |
| 13 | Portal | PIN login works — valid PIN accepted, invalid PIN rejected |  |
| 14 | Portal | Questions shuffle on each new session (test twice — order should differ) |  |
| 15 | Portal | Timer counts down correctly from set time |  |
| 16 | Portal | Score % calculates correctly (test with all-correct and known-wrong answers) |  |
| 17 | Portal | Pass threshold is 70% — confirmed (9/12 = pass, 8/12 = fail) |  |
| 18 | Portal | Teacher report shows correct/wrong for each question |  |
| 19 | Portal | Portal works offline (disconnect Wi-Fi → reload → still works) |  |
| 20 | Deployment | Live URL loads without errors and tested on a tablet |  |

# 9.  Deployment Steps

## 9.1  Add Route to index.js

Open index.js. Find the existing portal routes. Add one new line:

app.get('/multiplication-l5', (req,res) => res.sendFile(path.join(__dirname,'takmil-multiplication-level5-portal.html'))); Pattern: URL slug is topic-subject-level. Always lowercase, hyphens not spaces.

## 9.2  Git Deploy Commands

git add takmil-multiplication-level5-portal.html index.js git commit -m "Add Multiplication Level 5 assessment portal" git push origin main # Wait 1–2 minutes → Railway shows 'Deploy success' # Test: https://takmil-bot-production-0f51.up.railway.app/multiplication-l5

## 9.3  PIN Generation (run 3 times per portal — one per subject)

curl -X POST https://takmil-bot-production-0f51.up.railway.app/admin/pins/generate \ -H "Content-Type: application/json" \ -d '{"schoolId":1,"level":5,"subject":"Math","cohortSize":30,"issuedBy":"YourName"}' → Change subject to: Math / English / Urdu → Change level to match the portal (1–11) → Save all generated PINs to: Level[X]_[Subject]_PINs_[Date].txt → Share file with Project Manager

# 10.  Project Milestones & Timeline

Target: 4 new assessment portals per week (1 per content developer + 1 extra). At this pace all 255 portals complete in ~16 months. Accelerate by adding more content developers.

| Milestone | Week | Deliverable | Success Metric |
| --- | --- | --- | --- |
| M1 — Team Ready | 1–2 | All 6 team members onboarded, tools set up, training complete | Each member completes one test assessment end-to-end |
| M2 — Pipeline Proven | 3–4 | 10 assessments built, QA passed, deployed across Math/English/Urdu | 10 live portal URLs · PINs distributed to schools |
| M3 — L4–L7 Complete | 5–16 | All Level 4–7 assessments built (36 portals) | 100% teacher-approved · 100% QA-passed |
| M4 — L8–L11 Complete | 17–28 | All Level 8–11 assessments built (36 portals) | Full L1–L11 coverage across Math, English, Urdu |
| M5 — Video Library Done | Ongoing | All TAKMIL YouTube videos converted to assessments | Every video has a linked assessment portal |
| M6 — Full M&E Live | After M4 | Power BI dashboard showing assessment results by school/level/region | Shahid sees live data without asking anyone |

# 11.  Progress Tracker — Copy to Google Sheets

Create a Google Sheet with these columns. One row per video/assessment. PM fills in dates as each step completes.

| Video Title | YouTube URL | Level | Subject | Step 1URL Added | Step 2Q's Approved | Step 3Images OK | Step 4QA Passed | Step 5Deployed | Portal URL | PINsGenerated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Multiplication Intro | youtube.com/... | 5 | Math | ✓ Apr 20 | ✓ Apr 21 | N/A | ✓ Apr 22 | ✓ Apr 22 | /mult-l5 | ✓ |
| Jod Tod | youtube.com/... | 3 | Urdu | ✓ Apr 20 | ✓ Apr 21 | ✓ Apr 21 | ✓ Apr 22 | ✓ Apr 22 | /jod-tod | ✓ |
| [Next video] |  |  |  |  |  |  |  |  |  |  |

# 12.  Risks & How to Handle Them

| Risk | Likelihood | Fix |
| --- | --- | --- |
| YouTube video has no transcript / description too short | Medium | Fall back to curriculum PDF for that topic. Note in tracker: 'No transcript — used PDF' |
| Urdu questions contain errors not caught before deployment | Medium | Mandatory native Urdu speaker at Gate 1. QA Reviewer re-checks Urdu rendering in Chrome. |
| Answer text appears in an SVG image | Low | 3-layer architecture prevents this by design. Gate 2 human check adds safety layer. |
| Deployment Engineer pushes broken code — bot goes down | Low | Railway rollback: click previous successful deployment in Railway dashboard → Redeploy. |
| Team member leaves mid-project | Medium | Session summary document + tracker means any replacement can pick up from where they left. |
| Claude generates inaccurate questions | Low | All questions go through teacher Gate 1 review. Claude never goes directly to deployment. |

# 13.  Budget Estimate

| Item | Monthly | Annual | Notes |
| --- | --- | --- | --- |
| Claude.ai Pro (3 seats — one per subject developer) | $60 | $720 | $20/month × 3 content developers |
| Claude.ai Pro (PM + QA — optional) | $40 | $480 | Free tier may be sufficient for coordination |
| Railway hosting (existing) | ~$10 | ~$120 | Marginal increase with more portals |
| Google Workspace / Drive | $0 | $0 | Free tier sufficient |
| Human resources (6 people) | Project-specific | — | Costed separately per HR plan |
| TECH TOOLS TOTAL | ~$110/month | ~$1,320/year | Excluding human resources |

💡 Key insight: Building 255+ assessment portals costs less than $110/month in technology. This is under $0.50 per assessment portal — likely the lowest-cost assessment development system in the Pakistani education sector.

# 14.  How to Start — First Week Actions

- Shahid adds all 6 team members to GitHub repository and Railway dashboard

- Project Manager creates Google Sheet tracker using template in Section 11

- All Content Developers create Claude.ai Pro accounts

- Deployment Engineer clones the Railway repo locally — confirms git push works

- Full team reads this document — each person highlights their role sections

- Week 1 pilot: EACH team member independently builds ONE assessment end-to-end using a video Shahid selects — supervised by Shahid on a call

- Week 2: Team operates independently. PM assigns 4 videos per week. Build begins.

DOCUMENT APPROVED BY: Shahid Qamar ¦ Founder & CEO, TAKMIL Foundation DATE: April 2026 ¦ VERSION: 1.0 This document + the session summary = everything your team needs. Give them both. They can build the rest without you. Next step for Shahid: Share this document with your team and schedule the Week 1 kickoff call.